## Minute
Company A-Company B_Product1/2/3_Validation Weekly Meeting
회의록 저장 링크 |  |  | Date & Time: 12/10/2024 US (6:30am EST) 12/10/2024 Korea (8:30pm KST)
Call in number |  | +1 800-800-8001 | Facilitator: Gildong Hong |  | Location: MS teams
Upcoming Milestones
Time | Time Slot | Agenda | Presenter | Attachment | Discussion Summary/Action items
6:30 | 5 | Introduction/Agenda Review | Gildong Hong
6:35 | 5 | Safety Critical issue | Gildong Hong |  | None
6:40 | 10 | Timing | Gildong Hong |  | 12/10: 제품1: mile stone A를 맞출수 있음을 회사B가 알려주심. 대신 추가비용이 발생하며 PO로 전송할것임. Action item: 회사B가 PO를 12/12까지 전송하기 Action item: 회사A가 PO내부승인을 12/14까지 받고 알려주기 12/3: 제품1: Milestone A에 맞출지 의문. Action item: 회사B가 체크후 알려주심 제품2: 하기 critical issue#2발생으로 Milestone B에 영향 예상. Action item: GH이 내부보고후 회사B에 12/6까지 피드백공유 제품3: 하기 critical issue#1발생으로 Milestone A에 영향. Action item: GH이 내부보고후 회사B에 12/6까지 피드백공유
6:50 | 10 | Issue Summary | Malja Yeon |  | 12/3: 이슈 총 2개. 두개다 close target은 금주 말. Action item: 회사B가 원인분석을 수요일(12/11)까지 완료
7:00 | 10 | Critical issue#1 Deep dive | Choigo Kim |  | 12/3: 원인분석중. Fishbone diagram공유함. Action item: 회사A가 fishbone diagram과 보충자료 리뷰후 12/5까지 가이드제시
7:10 | 15 | Critical issue#2 Deep dive | Choigo Kim |  | 12/3: 오늘 발생. 총 12대중 2대. 내일부터 바로 시료분석. Action item: 회사B가 이슈 사진 전송(12/3). Action item: 회사A가 타 프로그램 에서 동일 이슈 이력이 있는지 12/4까지 알아보기
7:25 | 10 | Round Table | All |  | 12/3: 차주는 한국 휴일로 회의 없음.

## Action item List
Company A-Company B_Product1/2/3_Validation Weekly Meeting Action item List
Action item# | Priority | Action item Title | Description | Champion | Open date | Due date | Status | Attachment | Clousure date
1 | High | A를 체크하기 |  | Person A | 2025-05-20 | 2025-05-22 | 5/21: Complete |  | 2025-05-21
2 | Mid | B를 분석하기 |  | Person B | 2025-05-20 | 2025-05-31 | 5/20: D팀에게서 A데이터 받아야함. 5/28: Data받았고 5/30까지 분석완료예정
3 | Low | C를 검증하기 |  | Person A | 2025-05-20

## Meeting Attendance
A회사
Role | Name | Phone | Email | Attendance
Validation Group Manager
Sr. Validation Engineer |  |  |  | X
Component Validation Engineer |  |  |  | X
Component Validation Engineer
Component Validation Engineer |  |  |  | X
제품1/2/3 Design Engineer
B회사
Role | Name | Phone | Email | Attendance
제품1 Validation Engineer |  |  |  | X
제품2 Validation Engineer |  |  |  | X
제품3 Validation Engineer |  |  |  | X
제품1 Program Manager
제품2 Program Manager |  |  |  | X
제품3 Program Manager